## Slide 1: Project Selection
Homework
Calculate the payback period and ROI for the following three projects and suggest which one would you prefer and why.
Year | Project A | Project B | Project C
0 | -10 000 | -15 000 | -15 000
1 | 4 000 | 5 000 | 6 000
2 | 2 000 | 5 000 | 7 000
3 | 2 000 | 3 000 | 4 000
4 | -1 000 | 2 000 | 1 000
5 | 3 000 | 1 000 | -1 000
6 | 2 000 | 1 000 | -1 000

## Slide 2: Project Selection
Three main categories of methods/approaches:
  Strategic approach
  Analytical approach
  Financial methods

## Slide 3: Project Selection
Financial methods of project appraisal:
  Payback period
  “Time needed to get your money back”
  Return on investment
  Net Present Value (NPV)
  Internal Rate of Return (IRR)

## Slide 4: Project Selection
3. Net Present Value
Underlining idea:
  Our aim is to avoid the main weakness of both methods described earlier (the payback period and ROI)
  We have to take into account the time value of money.

## Slide 5: Net Present Value
Underlining idea:
It is clear that a 100,- CZK today will not have the same buying power as 100,- CZK next year because of
  inflation - we will need more money next year to buy the same product
  interest rates – having 100,- CZK this year I can put them on a saving account and to get the interest next year

## Slide 6: Net Present Value
Underlining idea:
For example, if the annual difference is 20%, then
  the value of 100,- CZK today
  will be 120,- CZK next year
  and 144,- CZK in two years time
  (because of compound interest calculation)
  100 * 1,2 = 120
  100 * 1,2 * 1,2 = 144
  100 * 1,2 * 1,2 * 1,2 = 172,8
  etc.

## Slide 7: Net Present Value
And, of course, it works vice versa as well
For example, if the annual difference is 20%, then
  the value of 120,- CZK next year
  is equal to 100,- CZK today
To put it in different words, if (assuming 20% annual difference) someone is going to give me 120,- CZK next year it is the same as getting 100,- CZK today
  120 / 1,2 = 100
  144 / (1,2 * 1,2) = 100
  172,8 / (1,2 * 1,2 * 1,2) = 100
  etc.

## Slide 8: Net Present Value
It is a straightforward way to express all future cash flows in terms of amount of money of the same worth today
The discount factor is derived from the reciprocal of the compound interest formula as
where r is the forecast interest rate and n is the number of years from start date.
There is no need to calculate it as the discount factors are readily available in the form of financial tables.

## Slide 9: Net Present Value
Table of discounting factors
Present value of 1 taking into account the interest rate r and number of years n
 | Interest rate r [%] |  |  |  |  |  |  |  |  |  | 
Y e a r s |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
 | 1 | 0,9901 | 0,9804 | 0,9709 | 0,9615 | 0,9524 | 0,9434 | 0,9346 | 0,9259 | 0,9174 | 0,9091
 | 2 | 0,9803 | 0,9612 | 0,9426 | 0,9246 | 0,9070 | 0,8900 | 0,8734 | 0,8573 | 0,8417 | 0,8264
 | 3 | 0,9706 | 0,9423 | 0,9151 | 0,8890 | 0,8638 | 0,8396 | 0,8163 | 0,7938 | 0,7722 | 0,7513
 | 4 | 0,9610 | 0,9238 | 0,8885 | 0,8548 | 0,8227 | 0,7921 | 0,7629 | 0,7350 | 0,7084 | 0,6830
 | 5 | 0,9515 | 0,9057 | 0,8626 | 0,8219 | 0,7835 | 0,7473 | 0,7130 | 0,6806 | 0,6499 | 0,6209
 | 6 | 0,9420 | 0,8880 | 0,8375 | 0,7903 | 0,7462 | 0,7050 | 0,6663 | 0,6302 | 0,5963 | 0,5645

## Slide 10: Net Present Value
Table of discounting factors
What is the present value of 1$ that I am going to get in 3 years from now taking into account the interest rate r=7%
 | Interest rate r [%] |  |  |  |  |  |  |  |  |  | 
Y e a r s |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
 | 1 | 0,9901 | 0,9804 | 0,9709 | 0,9615 | 0,9524 | 0,9434 | 0,9346 | 0,9259 | 0,9174 | 0,9091
 | 2 | 0,9803 | 0,9612 | 0,9426 | 0,9246 | 0,9070 | 0,8900 | 0,8734 | 0,8573 | 0,8417 | 0,8264
 | 3 | 0,9706 | 0,9423 | 0,9151 | 0,8890 | 0,8638 | 0,8396 | 0,8163 | 0,7938 | 0,7722 | 0,7513
 | 4 | 0,9610 | 0,9238 | 0,8885 | 0,8548 | 0,8227 | 0,7921 | 0,7629 | 0,7350 | 0,7084 | 0,6830
 | 5 | 0,9515 | 0,9057 | 0,8626 | 0,8219 | 0,7835 | 0,7473 | 0,7130 | 0,6806 | 0,6499 | 0,6209
 | 6 | 0,9420 | 0,8880 | 0,8375 | 0,7903 | 0,7462 | 0,7050 | 0,6663 | 0,6302 | 0,5963 | 0,5645

## Slide 11: Net Present Value
Example No. 1
Find the present value of $450 to be received 4 years from now at an interest rate of 8%.
Look up for the discount factor given in the table
For r=8 and n=4 it is 0.7350.
Thus the present value of $450 is
450*0.7350 = 330.75

## Slide 12: Net Present Value
Example No. 2
Using a discount rate of 15% find the present value of the cash flow
t=0 | t=1 | t=2 | t=3
-600 | 750 | -150 | 1050

## Slide 13: Net Present Value
Example No. 2
Using a discount rate of 15% find the present value of the cash flow
A convenient layout for the calculation is
Year | Cash Flow | Discount Factor | Present Value
0 | -600 |  | 
1 | 750 |  | 
2 | -150 |  | 
3 | 1050 |  | 

## Slide 14: Net Present Value
Example No. 2
The initial outlay has an associated discount factor equal to 1.0 because it is assumed that the initial outlay is payable immediately and so it is its own present value.
Year | Cash Flow | Discount Factor | Present Value
0 | -600 | 1.0000 | -600
1 | 750 |  | 
2 | -150 |  | 
3 | 1050 |  | 

## Slide 15: Net Present Value
Example No. 2
Fill in the remaining discount factors in the table
Calculate the relevant Present Values
Year | Cash Flow | Discount Factor | Present Value
0 | -600 | 1.0000 | -600.00
1 | 750 | 0.8696 | 652.20
2 | -150 | 0.7561 | -113.42
3 | 1050 | 0.6575 | 690.38

## Slide 16: Net Present Value
Example No. 2
Calculate the sum of present values
(total of the last column)
Year | Cash Flow | Discount Factor | Present Value
0 | -600 | 1.0000 | -600.00
1 | 750 | 0.8696 | 652.20
2 | -150 | 0.7561 | -113.42
3 | 1050 | 0.6575 | 690.38
Total Present Value |  |  | 629.16

## Slide 17: Net Present Value
Example No. 3
Using a discount rate of 10% find the present value of the cash flow
t=0 | t=1 | t=2 | t=3
-2200 | 770 | 968 | 1331

## Slide 18: Net Present Value
Example No. 3
Calculate the sum of present values
(total of the last column)
Year | Cash Flow | Discount Factor | Present Value
0 | -2200 |  | 
1 | 770 |  | 
2 | 968 |  | 
3 | 1331 |  | 
Total Present Value |  |  | 
1.0000
0.9091
0.8264
0.7513
-2200
800 (799,95)
+300
1000 (999,98)
700 (700.01)

## Slide 19: Net Present Value
Net Present Value (NPV) - Summary
The net present value (NPV) is the reverse of compound interest.
If you are offered 120,-CZK one year from now and the inflation & interest rate was 20%, working backwards its value in today terms will be 100,-CZK.
This is called the present value, and when the cash flows over a number of years are combined in this manner the total figure is called the net present value (NPV).

## Slide 20: Net Present Value
The formula for NPV is available in every spreadsheet.
If we have to calculate it manually the best setup is in the tabular form as we can see below:
Year | Cash Flow | Discount Factor | Present Value
0 | CF0 | DF0 | CF0*DF0
1 | CF1 | DF1 | CF1*DF1
… | …. | …. | ….
N | CFN | DFN | CFN*DFN
Net Present Value | ∑ CF*DF

## Slide 21: Net Present Value
The NPV is a measure of the value or worth added to the company by carrying out the project.
The decision rule can be expressed in the following form:
  If the NPV is positive the project merits further consideration.
  If the NPV is equal to zero it is indeterminate.
  If the NPV is negative the project should be rejected.

## Slide 22: Net Present Value
A negative NPV indicates that we would lose money by carrying out the relevant project.
  Nevertheless, it is your decision and you can still carry the project on because there are some other reasons to do so.
  At least, you know that you are going to lose your money.
When ranking the projects, preference should be given to the project with the highest NPV.

## Slide 23: Net Present Value
Assignment No. 4
Consider the same example as we did before, this time using NPV.
Assume the discounting factor r=20%.
Year | Machine A Cash Flow | Machine B Cash Flow
0 | -35000 | -35000
1 | 20000 | 10000
2 | 15000 | 10000
3 | 10000 | 15000
4 | 10000 | 20000

## Slide 24: Net Present Value
Results - Machine A
Year | Cash Flow | Discount Factor 20% | Present Value
0 | -35000 | 1.0000 | -35000
1 | 20000 | 0.8333 | 16666
2 | 15000 | 0.6944 | 10416
3 | 10000 | 0.5787 | 5787
4 | 10000 | 0.4823 | 4823
Total Present Value |  |  | 2692

## Slide 25: Net Present Value
Results - Machine B
Year | Cash Flow | Discount Factor 20% | Present Value
0 | -35000 | 1.0000 | -35000
1 | 10000 | 0.8333 | 8333
2 | 10000 | 0.6944 | 6944
3 | 15000 | 0.5787 | 8681
4 | 20000 | 0.4823 | 9646
Total Present Value |  |  | -1396

## Slide 26: Net Present Value
Results
The NPV for machine A is $2692
The NPV for machine B is -$1396.
NPV analysis suggests to select machine A in preference to machine B because it has a higher NPV.
Machine B would be rejected in any case because it has a negative NPV which means that the company would lose money by investing into this alternative.

## Slide 27: Net Present Value
The advantages of using NPV:
introduces time value of money
expresses all future cash flows in today’s values and therefore it enables direct comparison
takes into account inflation
looks at the whole project (from start to finish)
can stimulate project what-if analysis using different values
gives more accurate profit and loss forecast than non discounted cash flow (DCF) calculations

## Slide 28: Net Present Value
The disadvantages of using NPV:
its accuracy cannot be overestimated (it is limited by the accuracy of the predicted future cash flows and interest rates)
uses fixed interest rate over the duration of the project
quantifies profit in absolute terms while managers tend to prefer profitability expressed as a percentage

## Slide 29: Net Present Value
Assignment No. 5
calculate the payback period for both projects
calculate the ROI for both projects
calculate the NPV for both projects considering r=8% and r=10%
discuss the results and make a suggestion which project should be accepted by the top management of your company
Year | Machine A Cash Flow | Machine B Cash Flow
0 | -25000 | -15000
1 | 5000 | 7000
2 | 10000 | 5000
3 | 10000 | 3000
4 | 10000 | 3000

## Slide 30: Net Present Value
Assignment No. 5 - results
According to PB: no preference is given
According to ROI: A should be preferred
According to NPV: A should be preferred
Criteria | Machine A | Machine B
PB | 3 | 3
ROI | 10% | 5%
NPV8% | 3 491 | 354
NPV10% | 2 153 | -201

## Slide 31: Internal Rate of Return
4. Internal Rate of Return
The internal rate of return is also called DCF yield or DCF return on investment. The IRR is the value of discount when NPV is zero.
It is usually calculated by a trial and error method (even in MS Excel you will be asked for a guess to have some starting point).
We have to calculate NPV for various discount factors r and to increase it (if NPV > 0) or decrease it (if NPV < 0) in order to find the value of r when NPV is zero.

## Slide 32: Internal Rate of Return
4. Internal Rate of Return
The IRR analysis is a measure of the return on investment and therefore we should select the project with the highest IRR.
NPV
Discount factor r [%]
1. r=4% NPV = 1200
4
2. r=7% NPV = 600
7
15
3. r=15% NPV = 130
4. r=19% NPV = -25
5. r=18% NPV = 15
18
19
6. IIR > 18% & IIR < 19%
7. IIR = 18,63 % (interpolation)
IRR = 18,63%

## Slide 33: Internal Rate of Return
Example No. 6
Consider the same example as we did before, this time using IRR.
Year | Machine A Cash Flow | Machine B Cash Flow
0 | -35000 | -35000
1 | 20000 | 10000
2 | 15000 | 10000
3 | 10000 | 15000
4 | 10000 | 20000

## Slide 34: Internal Rate of Return
Example No. 6
Interest rate | Machine A NPV | Machine B NPV
14% | 6 756,39 | 3 432,78
15% | 6 026,15 | 2 554,90
16% | 5 318,31 | 1 708,01
17% | 4 631,93 | 890,70
18% | 3 966,12 | 101,66
19% | 3 320,04 | -660,38
20% | 2 692,90 | -1 396,60
21% | 2 083,94 | -2 108,15
22% | 1 492,44 | -2 796,07
23% | 917,71 | -3 461,39
24% | 359,10 | -4 105,06
25% | -184,00 | -4 728,00
26% | -712,19 | -5 331,07
27% | -1 226,04 | -5 915,09
IRR B
18,13%
IRR A
24,66%

## Slide 35: Internal Rate of Return
Example No. 6
IRR B
18,13%
IRR A
24,66%

## Slide 36: Internal Rate of Return
The advantages of using IRR:
takes into account the time value of money
looks at the whole project (from start to finish)
allows the manager to compare IRR with the current interest rates
the result is easy to understand and to interpret

## Slide 37: Internal Rate of Return
The disadvantages of using IRR:
little bit harder to calculate
mutual comparison of projects with different time duration is impossible
uses the same interest rate over the whole duration of the project

## Slide 38: Net Present Value
Calculations in MS Excel
NPV - Calculates the net present value of an investment by using a discount rate and a series of future payments (negative values) and income (positive values).
Syntax: NPV(rate,values)
Caution! The NPV investment begins one period before the date of the value1 cash flow and ends with the last cash flow in the list. The NPV calculation is based on future cash flows. If your first cash flow occurs at the beginning of the first period, the first value must be added to the NPV result, not included in the values arguments.

## Slide 39: Net Present Value
NPV – do not forget to include the initial outlay
„New“ syntax: NPV(rate,values)+Outlay

## Slide 40: Internal Rate of Return
Calculations in MS Excel
IRR
Returns the internal rate of return for a series of cash flows represented by the numbers in values.
Syntax: IRR(values,guess)

## Slide 41: Summary
Which method should I use?
Using a spreadsheet there is no reason why one should not use all the methods outlined here.
Payback period should be used as an initial filter, but not the only and solely method used.
It is definitely wise to use some DCF method to make sure that the time value of money is taken into consideration.
NPV should be used when comparing projects with uneven time duration.
NPV should be used in preference to IRR especially if you wish to vary interest rates over the years.
And finally - whichever method has been utilized do not forget that is your decision and your responsibility!

## Slide 42: Reality in manufacturing industry?
Financial appraisal criteria used
(based on the results of AMT Research conducted at FIM UHK)
Criteria used [%] | UK | USA | CZ | Total
PB | 68.5 | 39.3 | 63.5 | 57.2
ROI | 20.3 | 18.8 | 35.1 | 23.1
NPV | 52.4 | 41.0 | 45.9 | 47.0
IRR | 55.2 | 56.4 | 31.1 | 50.3
Number of methods used | UK | US | CZ | Total
1 | 17.5 | 23.1 | 23.0 | 20.7
2 | 29.4 | 34.2 | 32.4 | 31.7
3 | 32.9 | 34.2 | 20.3 | 30.5
4 or more | 20.3 | 8.5 | 24.3 | 17.1

## Slide 43: Net Present Value
Homework
calculate the payback period for both projects
calculate the ROI for both projects
calculate the NPV for both projects considering r=10% and r=12%
discuss the results and make a suggestion which project should be accepted by the top management of your company
Year | Machine A Cash Flow | Machine B Cash Flow
0 | -40000 | -70000
1 | 10000 | 30000
2 | 15000 | 20000
3 | 15000 | 20000
4 | 10000 | 20000
5 | 10000 | 10000