## Slide 1: Project Modelling
The success of the whole planning and control function depends on the project planner being able to define the project’s full scope of work precisely and accurately.
Project Definition
  Project can be defined as a group of activities that have to be performed in a logical sequence to meet preset objectives.

## Slide 2: Project Modelling
The Work Breakdown Structure (WBS) provides a useful tool to address this need efficiently.

## Slide 3: Project Modelling
The project is represented by a hierarchical structure that is designed to logically sub-divide all the work-elements of the project.

## Slide 4: Project Modelling
The goal of the project is placed at the top of the diagram and then it is sub-divide into smaller elements of work at each lower level of breakdown.

## Slide 5: Project Modelling
At the lowest level of the EBS the element of work is called work package.
Each element is identified by a short description.

## Slide 6: Project Modelling
The Work Breakdown Structure is useful for the general understanding of the project but we need a different view of the same structure in order to be able to make an efficient utilization of the breakdown structure.
We need to know which activities must be done in a specific order (precedence) and which activities could be done in parallel.
… a group of activities that have to be performed in a logical sequence ...

## Slide 7: Example: Stopping at Petrol Station
Construct dependency table for the following jobs in attending to a motor car at a service station
Activity | Description | Duration [sec] | Preceding activity
A | Driver arrives | 30 | 
B | Select brands of oil and petrol | 10 | 
C | Fill petrol tank | 120 | 
D | Prepare bill | 45 | 
E | Receive payment | 25 | 
F | Wash windscreens | 20 | 
G | Polish windscreens | 15 | 
H | Check tyre pressures | 80 | 
I | Inflate tyres | 100 | 
J | Open bonnet | 15 | 
K | Check oil requirements | 60 | 
L | Add oil | 25 | 
M | Add distilled water to battery | 30 | 
N | Fill radiator | 50 | 
O | Close bonnet | 5 | 
P | Driver departs | 10 | 

## Slide 8: Example: Stopping at Petrol Station
Construct dependency table for the following jobs in attending to a motor car at a service station
Activity | Description | Duration [sec] | Preceding activity
A | Driver arrives | 30 | None
B | Select brands of oil and petrol | 10 | 
C | Fill petrol tank | 120 | 
D | Prepare bill | 45 | 
E | Receive payment | 25 | 
F | Wash windscreens | 20 | 
G | Polish windscreens | 15 | 
H | Check tyre pressures | 80 | 
I | Inflate tyres | 100 | 
J | Open bonnet | 15 | 
K | Check oil requirements | 60 | 
L | Add oil | 25 | 
M | Add distilled water to battery | 30 | 
N | Fill radiator | 50 | 
O | Close bonnet | 5 | 
P | Driver departs | 10 | 

## Slide 9: Example: Stopping at Petrol Station
Construct dependency table for the following jobs in attending to a motor car at a service station
Activity | Description | Duration [sec] | Preceding activity
A | Driver arrives | 30 | None
B | Select brands of oil and petrol | 10 | A
C | Fill petrol tank | 120 | 
D | Prepare bill | 45 | 
E | Receive payment | 25 | 
F | Wash windscreens | 20 | 
G | Polish windscreens | 15 | 
H | Check tyre pressures | 80 | 
I | Inflate tyres | 100 | 
J | Open bonnet | 15 | 
K | Check oil requirements | 60 | 
L | Add oil | 25 | 
M | Add distilled water to battery | 30 | 
N | Fill radiator | 50 | 
O | Close bonnet | 5 | 
P | Driver departs | 10 | 

## Slide 10: Example: Stopping at Petrol Station
Construct dependency table for the following jobs in attending to a motor car at a service station
Activity | Description | Duration [sec] | Preceding activity
A | Driver arrives | 30 | None
B | Select brands of oil and petrol | 10 | A
C | Fill petrol tank | 120 | B
D | Prepare bill | 45 | 
E | Receive payment | 25 | 
F | Wash windscreens | 20 | 
G | Polish windscreens | 15 | 
H | Check tyre pressures | 80 | 
I | Inflate tyres | 100 | 
J | Open bonnet | 15 | 
K | Check oil requirements | 60 | 
L | Add oil | 25 | 
M | Add distilled water to battery | 30 | 
N | Fill radiator | 50 | 
O | Close bonnet | 5 | 
P | Driver departs | 10 | 

## Slide 11: Example: Stopping at Petrol Station
Construct dependency table for the following jobs in attending to a motor car at a service station
Activity | Description | Duration [sec] | Preceding activity
A | Driver arrives | 30 | None
B | Select brands of oil and petrol | 10 | A
C | Fill petrol tank | 120 | B
D | Prepare bill | 45 | C, L
E | Receive payment | 25 | 
F | Wash windscreens | 20 | 
G | Polish windscreens | 15 | 
H | Check tyre pressures | 80 | 
I | Inflate tyres | 100 | 
J | Open bonnet | 15 | 
K | Check oil requirements | 60 | 
L | Add oil | 25 | 
M | Add distilled water to battery | 30 | 
N | Fill radiator | 50 | 
O | Close bonnet | 5 | 
P | Driver departs | 10 | 

## Slide 12: Example: Stopping at Petrol Station
Construct dependency table for the following jobs in attending to a motor car at a service station
Activity | Description | Duration [sec] | Preceding activity
A | Driver arrives | 30 | None
B | Select brands of oil and petrol | 10 | A
C | Fill petrol tank | 120 | B
D | Prepare bill | 45 | C, L
E | Receive payment | 25 | D
F | Wash windscreens | 20 | A
G | Polish windscreens | 15 | F
H | Check tyre pressures | 80 | A
I | Inflate tyres | 100 | H
J | Open bonnet | 15 | A
K | Check oil requirements | 60 | J
L | Add oil | 25 | K, B
M | Add distilled water to battery | 30 | J
N | Fill radiator | 50 | J
O | Close bonnet | 5 | L, M, N
P | Driver departs | 10 | E, G, I, O

## Slide 13: Example: Stopping at Petrol Station
Draw the relevant network of activities using given precedencies.
Activity | Description | Duration [sec] | Preceding activity
A | Driver arrives | 30 | None
B | Select brands of oil and petrol | 10 | A
C | Fill petrol tank | 120 | B
D | Prepare bill | 45 | C, L
E | Receive payment | 25 | D
F | Wash windscreens | 20 | A
G | Polish windscreens | 15 | F
H | Check tyre pressures | 80 | A
I | Inflate tyres | 100 | H
J | Open bonnet | 15 | A
K | Check oil requirements | 60 | J
L | Add oil | 25 | K, B
M | Add distilled water to battery | 30 | J
N | Fill radiator | 50 | J
O | Close bonnet | 5 | L, M, N
P | Driver departs | 10 | E, G, I, O
Start
A
B
F
H
J
C
G
…
…
…
…
…
…

## Slide 14: Network analysis
In order to analyze the network, we need to include more pieces of information in a convenient form.
There is an convention that activities are represented as boxes. The box is subdivided to give information about the name/code of the activity, its duration, earliest start, latest start, earliest finish, latest finish and total float.
Early start |  | Early finish
Total Float | Activity Name | Duration
Late Start |  | Late Finish

## Slide 15: Network analysis
The earliest start for an activity is determined by the earliest finish of preceding activities.
Earliest finish is obtained by adding the activity duration.
Early start |  | Early finish
Total Float | Activity Name | Duration
Late Start |  | Late Finish

## Slide 16: Network analysis
The latest finish for an activity is determined by the latest start for succeeding activities.
The latest start is obtained by subtracting the activity duration.
The overall completion time for the project is the earliest finish for the last activity.
Early start |  | Early finish
Total Float | Activity Name | Duration
Late Start |  | Late Finish

## Slide 17: Network analysis
Example: Consider the following project and draw the activity network:
What is the overall completion time for this project?
Activity | Duration [hours] | Preceding activity
A | 2 | none
B | 4 | none
C | 4 | A
D | 6 | B
E | 4 | C, D

## Slide 18: Example
Draw the activity network including „dummy“ activities Start and End:
 |  |  |  |  |  |  | A | 2 |  |  |  | C | 4 |  |  |  |  |  |  |  |  |  | 
 |  | St | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  | E | 4 |  |  | End | 0 | 
 |  |  |  |  |  |  | B | 4 |  |  |  | D | 6 |  |  |  |  |  |  |  |  |  | 

## Slide 19: Example
Calculation of the earliest possible start and finish of each activity:
 |  |  |  |  |  |  | A | 2 |  |  |  | C | 4 |  |  |  |  |  |  |  |  |  | 
 |  | St | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  | E | 4 |  |  | End | 0 | 
 |  |  |  |  |  |  | B | 4 |  |  |  | D | 6 |  |  |  |  |  |  |  |  |  | 
0
0
0
0
2
2
6
4
4
10
10
14
14
14

## Slide 20: Example
We have completed the forward pass through the activity network:
 |  |  |  |  |  | 0 |  | 2 |  |  | 2 |  | 6 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | A | 2 |  |  |  | C | 4 |  |  |  |  |  |  |  |  |  | 
 | 0 |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 10 |  | 14 |  | 14 |  | 14 | 
 |  | St | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  | E | 4 |  |  | End | 0 | 
 |  |  |  |  |  | 0 |  | 4 |  |  | 4 |  | 10 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | B | 4 |  |  |  | D | 6 |  |  |  |  |  |  |  |  |  | 

## Slide 21: Example
Backward pass: calculation of the latest possible start and finish of each activity:
 |  |  |  |  |  |  | A | 2 |  |  |  | C | 4 |  |  |  |  |  |  |  |  |  | 
 |  | St | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  | E | 4 |  |  | End | 0 | 
 |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | B | 4 |  |  |  | D | 6 |  |  |  |  |  |  |  |  |  | 
0
0
0
2
2
6
4
4
10
10
14
14
14

## Slide 22: Example
Calculation of the earliest possible start and finish of each activity:
 |  |  |  |  |  |  | A | 2 |  |  |  | C | 4 |  |  |  |  |  |  |  |  |  | 
 |  | St | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  | E | 4 |  |  | End | 0 | 
 |  |  |  |  |  |  | B | 4 |  |  |  | D | 6 |  |  |  |  |  |  |  |  |  | 
0
0
0
0
2
2
6
4
4
10
10
14
14
14
14
14
14
10
10
10
6
6
4
4
4
0
0
0

## Slide 23: Example
We have completed the backward pass through the activity network:
 |  |  |  |  |  | 0 |  | 2 |  |  | 2 |  | 6 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | A | 2 |  |  |  | C | 4 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 4 |  | 6 |  |  | 6 |  | 10 |  |  |  |  |  |  |  |  |  | 
 | 0 |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 10 |  | 14 |  | 14 |  | 14 | 
 |  | St | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  | E | 4 |  |  | End | 0 | 
 | 0 |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 10 |  | 14 |  | 14 |  | 14 | 
 |  |  |  |  |  | 0 |  | 4 |  |  | 4 |  | 10 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | B | 4 |  |  |  | D | 6 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 0 |  | 4 |  |  | 4 |  | 10 |  |  |  |  |  |  |  |  |  | 

## Slide 24: Example
Calculate the float for each activity (=late start-early start):
 |  |  |  |  |  | 0 |  | 2 |  |  | 2 |  | 6 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 4 | A | 2 |  |  | 4 | C | 4 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 4 |  | 6 |  |  | 6 |  | 10 |  |  |  |  |  |  |  |  |  | 
 | 0 |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 10 |  | 14 |  | 14 |  | 14 | 
 | 0 | St | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 0 | E | 4 |  | 0 | End | 0 | 
 | 0 |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 10 |  | 14 |  | 14 |  | 14 | 
 |  |  |  |  |  | 0 |  | 4 |  |  | 4 |  | 10 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 0 | B | 4 |  |  | 0 | D | 6 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 0 |  | 4 |  |  | 4 |  | 10 |  |  |  |  |  |  |  |  |  | 

## Slide 25: Example
Indicate the critical path (activities whit zero float):
 |  |  |  |  |  | 0 |  | 2 |  |  | 2 |  | 6 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 4 | A | 2 |  |  | 4 | C | 4 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 4 |  | 6 |  |  | 6 |  | 10 |  |  |  |  |  |  |  |  |  | 
 | 0 |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 10 |  | 14 |  | 14 |  | 14 | 
 | 0 | St | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 0 | E | 4 |  | 0 | End | 0 | 
 | 0 |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 10 |  | 14 |  | 14 |  | 14 | 
 |  |  |  |  |  | 0 |  | 4 |  |  | 4 |  | 10 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 0 | B | 4 |  |  | 0 | D | 6 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 0 |  | 4 |  |  | 4 |  | 10 |  |  |  |  |  |  |  |  |  | 

## Slide 26: Example
Useful check-points:
  There is always at least one critical path
  The total float on each branch of the network remains constant
 |  |  |  |  |  | 0 |  | 2 |  |  | 2 |  | 6 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 4 | A | 2 |  |  | 4 | C | 4 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 4 |  | 6 |  |  | 6 |  | 10 |  |  |  |  |  |  |  |  |  | 
 | 0 |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 10 |  | 14 |  | 14 |  | 14 | 
 | 0 | St | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 0 | E | 4 |  | 0 | End | 0 | 
 | 0 |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 10 |  | 14 |  | 14 |  | 14 | 
 |  |  |  |  |  | 0 |  | 4 |  |  | 4 |  | 10 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 0 | B | 4 |  |  | 0 | D | 6 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 0 |  | 4 |  |  | 4 |  | 10 |  |  |  |  |  |  |  |  |  | 

## Slide 27: Critical Path Method/CPM
  1. Develop a list of activities that make up the project.
  2. Determine the immediate predecessor activities for each activity in the project.
  3. Estimate the completion time for each activity.
  4. Draw a network depicting the activities and immediate predecessors listed in steps 1 and 2.
  5. Using the network and activity time estimates, determine the earliest start time and earliest finish time for each activity by making forward pass through the network. The earliest finish time for the last activity in the project identifies the total time required to complete the project.
  6. Using the project completion time identified in step 5 as the latest finish time for the last activity, make backward pass through the network to identify the latest start time and latest finish time for each activity.
  7. Use difference between the latest start time and earliest start time for each activity to identify the slack time available for the activity.
  8. The critical path activities are the activities with zero slack.

## Slide 28: Critical Path Method/CPM
  Critical Path Method
  Determines the overall time needed for the project completion
  Facilitates the development of the activity schedule for the project
  Indicates critical activities
  Shows us how much time reserve (slack/float) we have for each activity
  Helps us to control and manage the relevant project

## Slide 29: Network analysis
Example 2:
Draw the network and identify the critical path.
Activity | Preceding Activity | Duration [weeks]
A | None | 7
B | None | 8
C | None | 6
D | A | 6
E | B | 6
F | B | 8
G | C | 4
H | D, E | 7
I | F, G, H | 3

## Slide 30: Network analysis
Example 2:
 |  |  |  |  |  | 0 |  | 7 |  |  | 7 |  | 13 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 1 | A | 7 |  |  | 1 | D | 6 |  |  | 14 |  | 21 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 1 |  | 8 |  |  | 8 |  | 14 |  |  | 0 | H | 7 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 14 |  | 21 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 8 |  | 14 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 0 | E | 6 |  |  |  |  |  |  |  | 21 |  | 24 |  |  | 24 |  | 24 | 
 | 0 |  | 0 |  |  | 0 |  | 8 |  |  | 8 |  | 14 |  |  |  |  |  |  |  | 0 | I | 3 |  |  | 0 | En | 0 | 
 | 0 | St | 0 |  |  | 0 | B | 8 |  |  |  |  |  |  |  |  |  |  |  |  | 21 |  | 24 |  |  | 24 |  | 24 | 
 | 0 |  | 0 |  |  | 0 |  | 8 |  |  | 8 |  | 16 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 5 | F | 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 13 |  | 21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 0 |  | 6 |  |  | 6 |  | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 11 | C | 6 |  |  | 11 | G | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 11 |  | 17 |  |  | 17 |  | 21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 31: Network analysis
Example 2:
CPM network provides us a very practical, easy and straightforward tool for project control and what if analysis.
What is likely to happen when …?
Activity B started 1 week later.
Activity D started on time (as scheduled) but due to some operational problems it takes one week more than estimated.
Activity I can be completed in 2 weeks only.

## Slide 32: Network analysis
Example 2:
Activity B started 1 week later.
  It will delay the whole project by one week.
 |  |  |  |  |  | 0 |  | 7 |  |  | 7 |  | 13 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 1 | A | 7 |  |  | 1 | D | 6 |  |  | 14 |  | 21 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 1 |  | 8 |  |  | 8 |  | 14 |  |  | 0 | H | 7 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 14 |  | 21 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 8 |  | 14 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 0 | E | 6 |  |  |  |  |  |  |  | 21 |  | 24 |  |  | 24 |  | 24 | 
 | 0 |  | 0 |  |  | 0 |  | 8 |  |  | 8 |  | 14 |  |  |  |  |  |  |  | 0 | I | 3 |  |  | 0 | En | 0 | 
 | 0 | St | 0 |  |  | 0 | B | 8 |  |  |  |  |  |  |  |  |  |  |  |  | 21 |  | 24 |  |  | 24 |  | 24 | 
 | 0 |  | 0 |  |  | 0 |  | 8 |  |  | 8 |  | 16 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 5 | F | 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 13 |  | 21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 0 |  | 6 |  |  | 6 |  | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 11 | C | 6 |  |  | 11 | G | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 11 |  | 17 |  |  | 17 |  | 21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 33: Network analysis
Example 2:
Activity D started on time (as scheduled) but due to some operational problems it takes one week more than estimated.
  It is not a problem and we can still complete it on time.
 |  |  |  |  |  | 0 |  | 7 |  |  | 7 |  | 13 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 1 | A | 7 |  |  | 1 | D | 6 |  |  | 14 |  | 21 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 1 |  | 8 |  |  | 8 |  | 14 |  |  | 0 | H | 7 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 14 |  | 21 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 8 |  | 14 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 0 | E | 6 |  |  |  |  |  |  |  | 21 |  | 24 |  |  | 24 |  | 24 | 
 | 0 |  | 0 |  |  | 0 |  | 8 |  |  | 8 |  | 14 |  |  |  |  |  |  |  | 0 | I | 3 |  |  | 0 | En | 0 | 
 | 0 | St | 0 |  |  | 0 | B | 8 |  |  |  |  |  |  |  |  |  |  |  |  | 21 |  | 24 |  |  | 24 |  | 24 | 
 | 0 |  | 0 |  |  | 0 |  | 8 |  |  | 8 |  | 16 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 5 | F | 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 13 |  | 21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 0 |  | 6 |  |  | 6 |  | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 11 | C | 6 |  |  | 11 | G | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 11 |  | 17 |  |  | 17 |  | 21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 34: Network analysis
Example 2:
Activity I can be completed in 2 weeks only.
  It could make the whole project one week shorter.
 |  |  |  |  |  | 0 |  | 7 |  |  | 7 |  | 13 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 1 | A | 7 |  |  | 1 | D | 6 |  |  | 14 |  | 21 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 1 |  | 8 |  |  | 8 |  | 14 |  |  | 0 | H | 7 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 14 |  | 21 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 8 |  | 14 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 0 | E | 6 |  |  |  |  |  |  |  | 21 |  | 24 |  |  | 24 |  | 24 | 
 | 0 |  | 0 |  |  | 0 |  | 8 |  |  | 8 |  | 14 |  |  |  |  |  |  |  | 0 | I | 3 |  |  | 0 | En | 0 | 
 | 0 | St | 0 |  |  | 0 | B | 8 |  |  |  |  |  |  |  |  |  |  |  |  | 21 |  | 24 |  |  | 24 |  | 24 | 
 | 0 |  | 0 |  |  | 0 |  | 8 |  |  | 8 |  | 16 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 5 | F | 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 13 |  | 21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 0 |  | 6 |  |  | 6 |  | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 11 | C | 6 |  |  | 11 | G | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 11 |  | 17 |  |  | 17 |  | 21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 35: Network analysis
Example 3:
Draw the network and identify the critical path.
Activity | Preceding Activity | Duration [weeks]
A | None | 5
B | A | 4
C | A | 7
D | A | 4
E | B | 5
F | C | 2
G | D | 4
H | E, F | 7

## Slide 36: Network analysis
Example 3:
What if analysis:
Activity B started 1 week later.
  It will delay the whole project by one week.
Activity G started 4 weeks later than scheduled.
  It is not a problem and we can still complete it on time.
Activity A can be completed in 3 weeks only.
  It could make the whole project 2 weeks shorter.
Activity C will be completed in 6 weeks only.
  There are two critical paths. Therefore, without further changes on the sub-path B-E there is no chance for shortening the total time of the project.

## Slide 37: Network analysis
Homework:
Draw the network and identify the critical path.
Activity | Preceding Activity | Duration [weeks]
A | None | 4
B | None | 6
C | A, B | 7
D | B | 8
E | B | 5
F | C | 5
G | D | 7
H | D, E | 8
I | F, G, H | 4