## Slide 1: Resource Smoothing - Homework
Activity | Preceding activity | Duration [weeks] | Staff Required
A | none | 2 | 2
B | none | 4 | 3
C | A | 3 | 2
D | A | 5 | 4
E | A | 1 | 3
F | C | 2 | 3
G | D | 5 | 3
H | B, E | 7 | 3
I | H | 2 | 2
J | F, G, I | 3 | 1

## Slide 2: Resource Smoothing - Homework
 |  |  |  |  |  | 0 |  | 2 |  |  | 2 |  | 5 |  |  | 5 |  | 7 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 1 | A | 2 |  |  | 6 | C | 3 |  |  | 6 | F | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 1 |  | 3 |  |  | 8 |  | 11 |  |  | 11 |  | 13 |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 0 |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 0 | St | 0 |  |  |  |  |  |  |  | 2 |  | 7 |  |  | 7 |  | 12 |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 0 |  | 0 |  |  |  |  |  |  |  | 1 | D | 5 |  |  | 1 | G | 5 |  |  |  |  |  |  | 13 |  | 16 |  | 16 |  | 16
 |  |  |  |  |  |  |  |  |  |  | 3 |  | 8 |  |  | 8 |  | 13 |  |  |  |  |  |  | 0 | J | 3 |  | 0 | En | 0
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 13 |  | 16 |  | 16 |  | 16
 |  |  |  |  |  |  |  |  |  |  | 2 |  | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 1 | E | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 3 |  | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 0 |  | 4 |  |  |  |  |  |  |  | 4 |  | 11 |  | 11 |  | 13 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 0 | B | 4 |  |  |  |  |  |  |  | 0 | H | 7 |  | 0 | I | 2 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 0 |  | 4 |  |  |  |  |  |  |  | 4 |  | 11 |  | 11 |  | 13 |  |  |  |  |  |  |  |  | 

## Slide 3: Resource Smoothing - Homework
All activities start as early as possible:
Time |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 
Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A |  | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | B |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  | 
 | C |  |  |  | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  | 
 | D |  |  |  | 4 | 4 | 4 | 4 | 4 |  |  |  |  |  |  |  |  |  | 
 | E |  |  |  | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | F |  |  |  |  |  |  | 3 | 3 |  |  |  |  |  |  |  |  |  | 
 | G |  |  |  |  |  |  |  |  | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 
 | H |  |  |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  | 
 | I |  |  |  |  |  |  |  |  |  |  |  |  | 2 | 2 |  |  |  | 
 | J |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 | 1 | 1 | 
Suma |  |  | 5 | 5 | 12 | 9 | 9 | 10 | 10 | 6 | 6 | 6 | 6 | 5 | 2 | 1 | 1 | 1 | 

## Slide 4: Resource Smoothing - Homework
Non-critical activity C has been delayed and the following activities too:
Time |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 
Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A |  | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | B |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  | 
 | C |  |  |  |  | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  | 
 | D |  |  |  | 4 | 4 | 4 | 4 | 4 |  |  |  |  |  |  |  |  |  | 
 | E |  |  |  | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | F |  |  |  |  |  |  |  | 3 | 3 |  |  |  |  |  |  |  |  | 
 | G |  |  |  |  |  |  |  |  | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 
 | H |  |  |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  | 
 | I |  |  |  |  |  |  |  |  |  |  |  |  | 2 | 2 |  |  |  | 
 | J |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 | 1 | 1 | 
Suma |  |  | 5 | 5 | 10 | 9 | 9 | 9 | 10 | 9 | 6 | 6 | 6 | 5 | 2 | 1 | 1 | 1 | 

## Slide 5: Resource Smoothing - Homework
Non-critical activities C and D have been delayed and the following activities too:
Time |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 
Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A |  | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | B |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  | 
 | C |  |  |  |  |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  |  | 
 | D |  |  |  |  | 4 | 4 | 4 | 4 | 4 |  |  |  |  |  |  |  |  | 
 | E |  |  |  | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | F |  |  |  |  |  |  |  |  |  |  |  |  | 3 | 3 |  |  |  | 
 | G |  |  |  |  |  |  |  |  |  | 3 | 3 | 3 | 3 | 3 |  |  |  | 
 | H |  |  |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  | 
 | I |  |  |  |  |  |  |  |  |  |  |  |  | 2 | 2 |  |  |  | 
 | J |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 | 1 | 1 | 
Suma |  |  | 5 | 5 | 6 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 1 | 1 | 1 | 

## Slide 6: Resource Smoothing - Homework
Two possible scenarios of resource smoothing:

## Slide 7: Crashing Durations
Network Analysis Results
Is the project completion time provided by CPM really the shortest possible?
  Based on the data provided there is no possibility to make the project duration shorter.
BUT
  What about if more people are available?
  What if new machinery can be employed?
  What is a different technology is applicable?
  How much money do we have?

## Slide 8: Crashing Durations
Case Study – Earthquake in CA
In January 1994, the Northridge earthquake in Southern California damaged ten bridges on the Santa Monica Freeway in Los Angeles.
C.C. Myers, Inc. won the contract to replace the bridges. The contract specified that the work had to be completed in 140 days.
The closure of the freeway was estimated to cost the economy of the area as much as $1M per day.

## Slide 9: Crashing Durations
Case Study – Earthquake in CA
The State of California, understanding the loss to the LA economy that was caused by the freeway being down, offered a $200,000 per day bonus for each day prior to the 140 days deadline
C.C. Myers, Inc. Took the challenge:
  Greatly expanded workforce (e.g. 134 ironworkers instead of 15)
  Special lighting equipment allowed them to work 24 hours a day
  Special materials were used in order to avoid weather influence
  Generous incentive scheme was introduced for teams of workers
  The work was scheduled as an „assembly line“ etc.

## Slide 10: Crashing Durations
Case Study – Earthquake in CA
With the cooperation and extra effort from Caltrans, the City of Los Angeles, the workers, and even the citizens of LA, the company completed the job in 66 days, a full 74 days ahead of schedule.
The $14.8M bonus is the largest early completion bonus paid by Caltrans.
It is evident that by adding more resources we can (sometimes) further shorten the project duration!

## Slide 11: Crashing Durations
Case Study – SureFlight
SureFlight Ground Services PLC has been providing a wide range of services at airports and to airline companies. Recently it has expanded its operations into the field of aircraft maintenance.
The Civil Aviation authorities require that all aircraft are subjected to rigorous maintenance inspection at stipulated regular intervals. The expansion is part of the long term strategy of SureFlight in accordance with its mission to be "... the leading provider of a complete range of high quality civil aircraft services... '.
The timing of the decision to proceed coincides with an opportunity to tender for a five year contract to provide the maintenance for the Airbus fleet of a major international passenger airline.

## Slide 12: Crashing Durations
Case Study – SureFlight
The requirements spelled out in the tender documents cover full maintenance of the aircraft engines, its airframe and fuel tanks and all landing gear.
After the aircraft has been checked in and all the relevant data recorded it will be moved to a maintenance hangar and positioned ready for work to begin. The first activities are concerned with conducting a detailed inspection of all the three areas of concern by suitably qualified inspection engineers.
From this a complete list of required rectifications is produced for the relevant fitters to perform. Once the rectifications have been done thorough checking is carried out before the aircraft is signed off and moved from the hangar ready to resume service.

## Slide 13: Crashing Durations
Case Study – SureFlight
Clearly it is desirable to minimize the loss of income incurred by the airline by completing the maintenance as quickly as possible.
However safety should never be compromised for the sake of shorter turnaround.
As a first step in the planning process the Project Manager developed a first level Work Breakdown Structure before proceeding to gather detailed data.
As the lower levels of the structure were produced and the work packages were broken down into activities vital data was recorded for later analysis. A summary of the activity data is given in Table 1

## Slide 14: Crashing Durations
Case Study – SureFlight
A summary of the activity data is given in Table 1:
Activity | Description | Preceding activity | Duration (days) | Inspection Engineers | Fitters
A | Position &jack up aircraft. Clean undercarriage & remove wheels | - | 2 | - | 4
B | Inspect engines | A | 2 | 1 | 3
C | Inspect airframe | A | 4 | 2 | 1
D | Inspect undercarriage | A | 2 | 1 | 3
E | Rectify airframe | C | 4 | - | 3
F | Rectify engines | B | 3 | - | 2
G | Rectify undercarriage & refit wheels | D | 4 | - | 1
H | Check rectification & sign off | E, F, G | 2 | 3 | 1

## Slide 15: Crashing Durations
Case Study – SureFlight
It is now possible to do some cost estimating based on the activity data using appropriate charge out rates for the engineers and fitters; in this case it was decided after consultation with the Accounts that $250 and $200 per day respectively should be used.
In addition some estimate of the costs of materials and spare parts that are likely to be used also needed including - the estimates are shown in Table 2 below.
Activity | A | B | D | E | G
Other Costs | 100 | 60 | 120 | 900 | 800

## Slide 16: Crashing Durations
Case Study – SureFlight
The estimated total costs for each activity including labor, materials and/or replacement parts is shown in Table 3.
Activity | Description | Preceding activity | Duration (days) | Estimated Cost
A | Position &jack up aircraft. Clean undercarriage & remove wheels | - | 2 | 1700
B | Inspect engines | A | 2 | 1760
C | Inspect airframe | A | 4 | 2800
D | Inspect undercarriage | A | 2 | 1820
E | Rectify airframe | C | 4 | 3300
F | Rectify engines | B | 3 | 1200
G | Rectify undercarriage & refit wheels | D | 4 | 1600
H | Check rectification & sign off | E, F, G | 2 | 1900

## Slide 17: Crashing Durations
CPM Application:
 |  |  |  |  |  | 2 |  | 4 |  |  |  | 4 |  | 7 |  |  |  |  |  |  |  | Act | Dur | Cost
 |  |  |  |  |  | 3 | B | 2 |  |  |  | 3 | F | 3 |  |  |  |  |  |  |  | A | 2 | 1700
 |  |  |  |  |  | 5 |  | 7 |  |  |  | 7 |  | 10 |  |  |  |  |  |  |  | B | 2 | 1760
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | C | 4 | 2800
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D | 2 | 1820
 | 0 |  | 2 |  |  | 2 |  | 6 |  |  |  | 6 |  | 10 |  |  | 10 |  | 12 |  |  | E | 4 | 3300
 | 0 | A | 2 |  |  | 0 | C | 4 |  |  |  | 0 | E | 4 |  |  | 0 | H | 2 |  |  | F | 3 | 1200
 | 0 |  | 2 |  |  | 2 |  | 6 |  |  |  | 6 |  | 10 |  |  | 10 |  | 12 |  |  | G | 4 | 1600
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | H | 2 | 1900
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total | 12 | 16080
 |  |  |  |  |  | 2 |  | 4 |  |  |  | 4 |  | 8 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 2 | D | 2 |  |  |  | 2 | G | 4 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 4 |  | 6 |  |  |  | 6 |  | 10 |  |  |  |  |  |  |  |  |  | 
Normal scenario:
CP: A-C-E-H
Time: 12, Cost: 16080

## Slide 18: Crashing Durations
Case Study – SureFlight
Exercise:
What is the total project time?
What is the critical path?
Consider each of the following and discuss their individual effects on the total project time:
a) extra work is required on the undercarriage (G) which will take one day longer than expected
b) inspection and rectification of airframe (C & E) takes only 6 days
c) due to an emergency on an operational aircraft the engine inspection (B) is delayed and does not start until the beginning of the 7th day
 |  |  |  |  | 2 |  | 4 |  |  |  | 4 |  | 7 |  |  |  |  | 
 |  |  |  |  | 3 | B | 2 |  |  |  | 3 | F | 3 |  |  |  |  | 
 |  |  |  |  | 5 |  | 7 |  |  |  | 7 |  | 10 |  |  |  |  | 
0 |  | 2 |  |  | 2 |  | 6 |  |  |  | 6 |  | 10 |  |  | 10 |  | 12
0 | A | 2 |  |  | 0 | C | 4 |  |  |  | 0 | E | 4 |  |  | 0 | H | 2
0 |  | 2 |  |  | 2 |  | 6 |  |  |  | 6 |  | 10 |  |  | 10 |  | 12
 |  |  |  |  | 2 |  | 4 |  |  |  | 4 |  | 8 |  |  |  |  | 
 |  |  |  |  | 2 | D | 2 |  |  |  | 2 | G | 4 |  |  |  |  | 
 |  |  |  |  | 4 |  | 6 |  |  |  | 6 |  | 10 |  |  |  |  | 

## Slide 19: Crashing Durations
SureFlight – Improving our plan
Each of the activities involved was examined in turn and alternative "crash" durations, together with the necessary resources and costs were estimated. These are shown below:
What are the possibilities to improve our plan?
Activity | Crash Duration | Inspection Engineers | Fitters | Estimated Cost ($)
A | 1 | - | 9 | 1900
C | 2 | 2 | 6 | 3000
E | 3 | - | 6 | 4500
F | 2 | - | 4 | 1600
G | 2 | - | 3 | 2000

## Slide 20: Improving our plan
Case Study – SureFlight
We need to update our table with data first:
Activity | Description | Preceding activity | Duration (days) | Estimated Cost | Crash Duration | New Cost
A | Position &jack up aircraft. | - | 2 | 1700 | 1 | 1900
B | Inspect engines | A | 2 | 1760 | -- | --
C | Inspect airframe | A | 4 | 2800 | 2 | 3000
D | Inspect undercarriage | A | 2 | 1820 | -- | --
E | Rectify airframe | C | 4 | 3300 | 3 | 4500
F | Rectify engines | B | 3 | 1200 | 2 | 1600
G | Rectify undercarriage &refit wheels | D | 4 | 1600 | 2 | 2000
H | Check rectification & sign off | E, F, G | 2 | 1900 | -- | --

## Slide 21: Improving our plan
We have to calculate the cost of the time that could be saved.
We are interested in cost per day being saved
Cost per day saved = additional cost/number of days saved
Activity | Duration (days) | Estimated Cost | Crash Duration | New Cost | Days Saved | Additional Cost | Cost per „Day Saved“
A | 2 | 1700 | 1 | 1900 | 1 | 200 | 
B | 2 | 1760 | -- | -- | -- | -- | ---
C | 4 | 2800 | 2 | 3000 | 2 | 200 | 
D | 2 | 1820 | -- | -- | -- | -- | ---
E | 4 | 3300 | 3 | 4500 | 1 | 1200 | 
F | 3 | 1200 | 2 | 1600 | 1 | 400 | 
G | 4 | 1600 | 2 | 2000 | 2 | 400 | 
H | 2 | 1900 | -- | -- | -- | -- | ---
200/1=200
200/2=100
1200/1=1200
400/1=400
400/2=200

## Slide 22: Improving our plan
In order to improve the plan it is necessary to select an activity on critical path that could be done in shorter time
Our critical path is A-C-E-H (three options)
If there are more choices available, choose the cheapest solution
Activity | Duration (days) | Estimated Cost | Crash Duration | New Cost | Days Saved | Additional Cost | Cost per „Day Saved“
A | 2 | 1700 | 1 | 1900 | 1 | 200 | 200
B | 2 | 1760 | -- | -- | -- | -- | --
C | 4 | 2800 | 2 | 3000 | 2 | 200 | 100
D | 2 | 1820 | -- | -- | -- | -- | --
E | 4 | 3300 | 3 | 4500 | 1 | 1200 | 1200
F | 3 | 1200 | 2 | 1600 | 1 | 400 | 400
G | 4 | 1600 | 2 | 2000 | 2 | 400 | 200
H | 2 | 1900 | -- | -- | -- | -- | --

## Slide 23: Improving our plan
CPM Application:
The scenario created by our decision to crash C:
 |  |  |  |  |  | 2 |  | 4 |  |  |  | 4 |  | 7 |  |  |  |  |  |  |  | Act | Dur | Cost | Crashed
 |  |  |  |  |  | 1 | B | 2 |  |  |  | 1 | F | 3 |  |  |  |  |  |  |  | A | 2 | 1700 | 
 |  |  |  |  |  | 3 |  | 5 |  |  |  | 5 |  | 8 |  |  |  |  |  |  |  | B | 2 | 1760 | N/A
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | C | 2 | 3000 | yes
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D | 2 | 1820 | N/A
 | 0 |  | 2 |  |  | 2 |  | 4 |  |  |  | 4 |  | 8 |  |  | 8 |  | 10 |  |  | E | 4 | 3300 | 
 | 0 | A | 2 |  |  | 0 | C | 2 |  |  |  | 0 | E | 4 |  |  | 0 | H | 2 |  |  | F | 3 | 1200 | 
 | 0 |  | 2 |  |  | 2 |  | 4 |  |  |  | 4 |  | 8 |  |  | 8 |  | 10 |  |  | G | 4 | 1600 | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | H | 2 | 1900 | N/A
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total | 10 | 16280 | 
 |  |  |  |  |  | 2 |  | 4 |  |  |  | 4 |  | 8 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 0 | D | 2 |  |  |  | 0 | G | 4 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 2 |  | 4 |  |  |  | 4 |  | 8 |  |  |  |  |  |  |  |  |  |  | 
Scenario “crash C”:
CP: A-C-E-H & A-D-G-H
Time: 10, Cost: 16280

## Slide 24: Improving our plan
Select an activity on critical path that could be done in shorter time and if there are more choices available, choose the cheapest solution by means of cost per day saved
Critical pathes: A-C-E-H & A-D-G-H
Activity | Duration (days) | Estimated Cost | Crash Duration | New Cost | Days Saved | Additional Cost | Cost per „Day Saved“
A | 2 | 1700 | 1 | 1900 | 1 | 200 | 200
B | 2 | 1760 | -- | -- | -- | -- | --
C | 4 | 2800 | 2 | 3000 | 2 | 200 | 100
D | 2 | 1820 | -- | -- | -- | -- | --
E | 4 | 3300 | 3 | 4500 | 1 | 1200 | 1200
F | 3 | 1200 | 2 | 1600 | 1 | 400 | 400
G | 4 | 1600 | 2 | 2000 | 2 | 400 | 200
H | 2 | 1900 | -- | -- | -- | -- | --

## Slide 25: Improving our plan
CPM Application:
The scenario created by our decision to crash C and then A:
 |  |  |  |  | 1 |  | 3 |  |  |  | 3 |  | 6 |  |  |  |  |  |  |  | Act | Dur | Cost | Crashed
 |  |  |  |  | 1 | B | 2 |  |  |  | 1 | F | 3 |  |  |  |  |  |  |  | A | 1 | 1900 | yes
 |  |  |  |  | 2 |  | 4 |  |  |  | 4 |  | 7 |  |  |  |  |  |  |  | B | 2 | 1760 | N/A
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | C | 2 | 3000 | yes
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D | 2 | 1820 | N/A
0 |  | 1 |  |  | 1 |  | 3 |  |  |  | 3 |  | 7 |  |  | 7 |  | 9 |  |  | E | 4 | 3300 | 
0 | A | 1 |  |  | 0 | C | 2 |  |  |  | 0 | E | 4 |  |  | 0 | H | 2 |  |  | F | 3 | 1200 | 
0 |  | 1 |  |  | 1 |  | 3 |  |  |  | 3 |  | 7 |  |  | 7 |  | 9 |  |  | G | 4 | 1600 | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | H | 2 | 1900 | N/A
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total | 9 | 16480 | 
 |  |  |  |  | 1 |  | 3 |  |  |  | 3 |  | 7 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | 0 | D | 2 |  |  |  | 0 | G | 4 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | 1 |  | 3 |  |  |  | 3 |  | 7 |  |  |  |  |  |  |  |  |  |  | 
Scenario “crash C&A”:
CP: A-C-E-H & A-D-G-H
Time: 9, Cost: 16480

## Slide 26: Improving our plan
Select an activity on critical path that could be done in shorter time and ff there are more choices available, choose the cheapest solution by means of cost per day saved
Critical pathes: A-C-E-H & A-D-G-H
Activity | Duration (days) | Estimated Cost | Crash Duration | New Cost | Days Saved | Additional Cost | Cost per „Day Saved“
A | 2 | 1700 | 1 | 1900 | 1 | 200 | 200
B | 2 | 1760 | -- | -- | -- | -- | --
C | 4 | 2800 | 2 | 3000 | 2 | 200 | 100
D | 2 | 1820 | -- | -- | -- | -- | --
E | 4 | 3300 | 3 | 4500 | 1 | 1200 | 1200
F | 3 | 1200 | 2 | 1600 | 1 | 400 | 400
G | 4 | 1600 | 2 | 2000 | 2 | 400 | 200
H | 2 | 1900 | -- | -- | -- | -- | --

## Slide 27: Improving our plan
CPM Application:
The scenario created by our decision to crash A, C, E, and G:
 |  |  |  |  | 1 |  | 3 |  |  |  | 3 |  | 6 |  |  |  |  |  |  |  | Act | Dur | Cost | Crashed
 |  |  |  |  | 0 | B | 2 |  |  |  | 0 | F | 3 |  |  |  |  |  |  |  | A | 1 | 1900 | yes
 |  |  |  |  | 1 |  | 3 |  |  |  | 3 |  | 6 |  |  |  |  |  |  |  | B | 2 | 1760 | N/A
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | C | 2 | 3000 | yes
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D | 2 | 1820 | N/A
0 |  | 1 |  |  | 1 |  | 3 |  |  |  | 3 |  | 6 |  |  | 6 |  | 8 |  |  | E | 3 | 4500 | yes
0 | A | 1 |  |  | 0 | C | 2 |  |  |  | 0 | E | 3 |  |  | 0 | H | 2 |  |  | F | 3 | 1200 | 
0 |  | 1 |  |  | 1 |  | 3 |  |  |  | 3 |  | 6 |  |  | 6 |  | 8 |  |  | G | 2 | 2000 | yes
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | H | 2 | 1900 | N/A
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total | 8 | 18080 | 
 |  |  |  |  | 1 |  | 3 |  |  |  | 3 |  | 5 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | 1 | D | 2 |  |  |  | 1 | G | 2 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | 2 |  | 4 |  |  |  | 4 |  | 6 |  |  |  |  |  |  |  |  |  |  | 
Scenario “crash C,A+E&G”:
CP: A-B-F-H & A-C-E-H
Time: 8, Cost: 18080

## Slide 28: Improving our plan
There is only one possibility for crashing remaining (F) but it will shorten just one of two critical paths and total time will stay the same (8 days, but the cost will rise by another 400 )
There is no further improvement possible
Activity | Duration (days) | Estimated Cost | Crash Duration | New Cost | Days Saved | Additional Cost | Cost per „Day Saved“
A | 2 | 1700 | 1 | 1900 | 1 | 200 | 200
B | 2 | 1760 | -- | -- | -- | -- | --
C | 4 | 2800 | 2 | 3000 | 2 | 200 | 100
D | 2 | 1820 | -- | -- | -- | -- | --
E | 4 | 3300 | 3 | 4500 | 1 | 1200 | 1200
F | 3 | 1200 | 2 | 1600 | 1 | 400 | 400
G | 4 | 1600 | 2 | 2000 | 2 | 400 | 200
H | 2 | 1900 | -- | -- | -- | -- | --

## Slide 29: Improving our plan
Was our effort worthwhile? What is the result?
Normal scenario:
CP: A-C-E-H
Time: 12, Cost: 16 080
Scenario “crash C”:
CP: A-C-E-H & A-D-G-H
Time: 10, Cost: 16 280
Scenario “crash C&A”:
CP: A-C-E-H & A-D-G-H
Time: 9, Cost: 16 480
Scenario “crash C,A+E&G”:
CP: A-B-F-H & A-C-E-H
Time: 8, Cost: 18 080

## Slide 30: Crashing Durations
Important notes:
There are limits as to how much speed can be gained by adding staff. Doubling the size of the workforce will not necessarily reduce completion time by half – issues of training, communication within larger team, problem of co-ordination etc.
These problems could be solved by scheduling overtime (no additional costs of coordination and communication) but it has many disadvantages too.
It is not true that over an extended period of time, a person productivity remains constant. There are natural limits to what is possible and extended overtime may actually lead to an overall decline in productivity.

## Slide 31: Homework
A project is described by the activities A to F in the table below. Also given are the predecessor activities, times required and costs for a normal and a crash program for each activity.
a) Draw the network diagram and carry out the analysis using the normal times and costs.
b) Find the time-cost trade-off points that are possible. What is the minimum time in which the program can be completed and what is the cost of this program.
Activity | Predecessors | Normal Duration | Cost $ | Crash Duration | Cost $
A | - | 8 | 100 | 6 | 200
B | - | 4 | 150 | 2 | 350
C | A | 2 | 50 | 1 | 90
D | A | 10 | 100 | 5 | 400
E | B | 5 | 100 | 1 | 200
F | C, E | 3 | 80 | 1 | 100