## Slide 1: Event Management
Has all the characteristics of a project
The ultimate feature is the time-limited scheduling because the date of the event cannot be adjusted
If the project is late (one day, one hour or even one minute), the whole event is usually missed
  Wedding/family celebration/party
  Business trip/holiday
  Conference/exhibition/concert
  Sport match/championship/olympics

## Slide 2: Event Management
There is usually a very long preparation phase followed by a very short implementation phase
The ultimate feature is the time-limited scheduling
  Proper wedding is usually planned several months in advance and it takes one day only
  Olympic games are being prepared for eight years while the competition phase takes less than three weeks
We will utilize the event management to show and explain some further parts of project management

## Slide 3: Event Management
At the very beginning of any event (project) it is good to answer the following important questions (5W):
Why? What is the purpose of the event?
Who? Who are the participants or stakeholders?
When? The date of the event.
Where? The place of the event.
What? What are the details of the event and expectations?
Based on the answers to the questions listed above we can understand the basic features and the scope of the event.

## Slide 4: Event Management
Event planning should cover the following issues
Work breakdown structure including responsibilities
Work schedule and deadlines
Costing and budgeting
Procurement plans
Risk considerations and the relevant responses
Action plan of the event management

## Slide 5: Work breakdown
Wedding
Venue
Invitation
Outfits
….
Church
Reception
Service
Rings
Choir
Flowers
Meals
Drinks
Speeches
Music
Guest list
Invitations
Distribut.
RSVP
Bride
Maids
Groom
Dress
Shoes
Flowers
Dress
Shoes
Hat
Corsage
Dress
Shoes
Hair
Flowers

## Slide 6: Work breakdown
It is possible to create the traditional network diagram and to analyze it using CPM, but we will look at it from a different perspective now
We will create the event checklist that shows activities and links them with responsibilities, budget, procurement, resources as well as potential risk
Activity | Responsibility | Budget | Procure | Resource | Risk
Rings | Groom | 25 000 | Rings | --- | Forgetting them
Choir | Bride’s mother | 8 000 | Choir | Choir mbrs. | Do not come
Reception | Bride’s father | 50 000 | Catering | Waiters | Rain/Too hot
Music | Groom | 1000 | Dance music | DJ | Gets drunk
… |  |  |  |  | 

## Slide 7: Procurement
Procurement is the process of acquiring necessary goods, products and services
The procurement schedule must be considered right after the network diagram has been established as it is possible that procurement of some specific items could take a very long time and therefore it could delay the start of the relevant activities
Procurement List | Date Required | Lead Time | Order By Date
Church | One day before wedding | 2 months | 
Flowers | Two hours before wedding | 2 weeks | 
Cars | One hour before wedding | 2 weeks | 
Hotel/Reception | Wedding day | 6 months | 
….. |  |  | 

## Slide 8: Resource Management
Resource management is the process of co-ordinating manpower and machine requirements
It is typical that during the preparation phase the manpower requirements are low while the numbers dramatically increase during the event
Considering the wedding case, we have to consider the number of cars, drivers, parking assistants, waiters, cleaners, …. as well as their availability during the whole event
For example, all cars and drivers will be needed during the transportation from the church to the hotel, while less cars and drivers will be needed later that evening (not everyone is leaving at the same time)

## Slide 9: Risk Management
Murphy's law: "things will go wrong in any given situation, if you give them a chance," or "whatever can go wrong, will go wrong"
Good project managers are anticipating risks because there are many unpredictable factors that could influence our event
We wish to run everything as smoothly as possible on the day of the event
It is normal that there is a real rush on behind the scenes, but we don’t want our guests to notice any problem
That is why we have to be well prepared and everything should be carefully rehearsed and backed up

## Slide 10: Risk Management
The objective of risk management is to minimize the chances of project failure
Risk management is the process of identifying, analyzing and responding to project risk
In order to face the risk we have to
Identify risk – areas of risk, uncertainties, and constraints
Quantify risk – in terms of impact as well as frequency
Develop response – how are we going to respond (eliminate, mitigate, deflect, accept)

## Slide 11: Risk Response
Risk elimination avoids the risk completely (removing the case, alternative scenarios, reducing the scope of the project)
Risk mitigation means reducing the probability of risk and its impact (increased control, more reliable people/technology, reducing complexity)
Risk deflection means transferring the risk to another party (by contracting, buying insurance, warranties)
Risk acceptance means that you ready to accept the consequences of the risk occurring. However, there are usually some contingency plans (what-if) as well as contingency budget
Usually more than one response is under consideration

## Slide 12: Risk Management
Project (event) risk management table shows how risk can influence the individual activities and the measures that we prepared in order to handle it
Activity | Responsibility | Risk | Impact | Response
Bridal dress | Bride | Is not ready | High | Timely fitting, early delivery date
Rings | Groom | Forgetting them | High | Best man to check it
Choir | Bride’s mother | Do not get together | Medium | Reproduced music
Reception | Bride’s father | Rain/Too hot | High | Contingency plans by catering agency
Music | Groom | DJ gets drunk | Low | Keep an eye on him, replace him
… |  |  |  | 

## Slide 13: Event Management
Monitoring and Controlling
In contrary to general project management where the manager monitors the execution process and has usually many opportunities to take corrective actions, there is no such luxury in the case of event management
Event managers have to react immediately when the event is in full swing and that is why it is so important to be prepared and react according to the prepared plans
And of course, because something unexpected always could arise, we have to take the opportunity to learn from each event in order to make the next one better

## Slide 14: Event Management
And finally …
We must not forget that to close down the event properly
Participants have to leave (cars, queues, crowds, safety measures …)
The place has to be cleaned and returned to normal
All the bills have to be paid
It is good to ask the stakeholders and to find out whether we met their expectations
We have to learn our post-event lessons to avoid the same mistakes next time

## Slide 15: Event Management
Altogether …
We can see that event management is a special kind of project management where especially time considerations are crucial
Otherwise the same project management scheme could be followed:
1. Initiation process (event is defined, starting phase)
2. Event planning process (from 5W up to the action plan)
3. Executing process (our big day is here)
4. Monitoring and controlling process (keep it on the track)
5. Closing process (it is over, but not yet for us)

## Slide 16: Event Management
You are required to organize an event
Book or career fair
Press conference
Concert, conference, fashion show
Party or family celebration
Sport competition or tournament
Teambuilding activity
Weekend city break
… … please select a suitable event.

## Slide 17: Event Management
Discuss and prepare at least a partial relevant work breakdown table, identify the potential risk and suggest the adequate measures in order to cope with that risk:
Activity | Responsibility | Risk | Impact | Response

## Slide 18: Homework
Please identify three most widespread beliefs (stereotypes) associated with the nation/culture you are coming from.
Can you see some typical Czech stereotypes/peculiarities?